## Steps
Implementation Steps
Objectives | Notes
Step 1 ¦ Kickoff
Solidify program parameters
Establish enrollment month
Establish funding month
Establish roles and responsibilities
Communicate next steps
Step 2 ¦ Communications
Establish plan ¦ channel, timing, audience, content
Documents and/or copy needed from BenefitEd ¦ flyers, email copy, intranet copy
Enrollment and Enrollment Confirmation email review and feedback
Co-Branding
Step 3 ¦ Training
Administrative duties and responsibilities
Program cycle
Functionalities of Employer Portal
Employee Enrollment ¦ demonstration and important considerations
Step 4 ¦ Testing
Draft of Eligibility File
Enrollment and Enrollment Confirmation email
Step 5 ¦ Launch
Upload Eligibility File to Employer Portal
Enrollment emails sent to Employees
Employees enroll

## Check List
Implementation Check List
Task | Department(s) Involved | Responsible Owner | Target Completion Date | Completion Date | Additional Notes
Setup
Setup GL account for employee payroll deductions for student loans | Payroll
Setup GL account for transaction fees | Accounting
Setup internal payment process for monthly invoice | Accounting
Setup memo/earnings & deduction code in HRIS/Payroll | Payroll
Add new accounts to GL through HRIS | Payroll
Identify taxability of benefit | Payroll
Whitelist BenefitEd's IP Address 168.245.65.26 and email benefited@nelnet.com | HR/IT
Identify ACH Pull or ACH Push | Accounting
If ACH Pull, send BenefitEd bank letter or voided check for banking info. | Accounting
If ACH Push, acquire BenefitEd's W-9 or identify items needed with Account Manager | Accounting
Review and approve company account information via BenefitEd platform | Admin.
Create credentials for employer portal via BenefitEd platform | Admin.
Create credentials for employer portal via BenefitEd platform | User(s)
Communication
Develop communication plan with BenefitEd | Marketing/HR
Acquire communication pieces from BenefitEd (i.e. flyers, email copy) | Marketing/HR
Execute communication to employees | Marketing/HR
Update benefits communication to include BenefitEd | HR/Benefits
Review and approve BenefitEd email communications to eligible employees | Marketing/HR
Training
Training on Employer Portal | HR/Benefits
Training on Employee Enrollment | HR/Benefits
Create Eligibility File of employees based off of set parameters | HR/IT
Send draft of Eligibility File to BenefitEd Account Manager for review | HR/Benefits
Create Enrollment Goal Plan | Admin. and Account Manager
Launch
Upload Eligibility File through Employer Portal | Admin.

## Sample Eligibility File
FirstName | LastName | Email | Phone | EmployeeID | StartDate | CurrentRetirementAllocation% | YTDEmployer401kContribution | CurrentEligibleCompensation
Jane | Doe | jane.doe@company.com | 555-555-5555 | 2222 | 2019-01-01 | 1 | 0 | 4500

## Sample Payroll File
EmployeeID | FirstName | LastName | StudentLoanDeduction$ | RetirementDeduction% | YTDEmployer401kContribution | CurrentEligibleCompensation
2222 | Jane | Doe | 100 | 0 | 0 | 4500

## Sample Elections File
First Name | Last Name | Employee ID | Payroll Deduction | Contribution Type
Jane | Doe | 2222 | 100 | Dollar

## Sample Match File
First Name | Last Name | Employee Id | Employee Contribution | Employer Match
Jane | Doe | 2222 | 100 | 100

## Sheet1 (hidden)
Completed
In Progress
Scheduled